## CL
ACTIVITIES | [11 empty] | Month 1 | [19 empty] | Month 2 | [30 empty] | Indicators | Means of verification | Implementation status (Done, In progress, Not done) | Responsibles | Remarks
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Before the campain Before campaign | SBC ACTIVITIES
Conduct preparation and coordination meetings for SBC interventions.
Microplanning of social mobilizationn activities.
Updating the behavioral plan (communication, advocay and social mobilization strategies) for the polio outbreak response
Development of the campaign's digital communication plan
Development of messages bank and advocacy packages for stakeholders
Poster, banner and leaflet design
Development/review of SBC data management tools for the campaign
Conduct a rapid capacity assessment of SBC supervisos and social mobilizers.
Develop and pretest social mobilization training modules based on the capacity assessment.
Validating campaign data management tools
Approve social mobilization training modules
Ordering and production of communication materials (banners, advocacy kits, megaphones) + visibility materials.
Conduct community dialogue focusing on hesitant groups
Training bloggers for digital social mobilization
Launch of digital awareness campaign
Design and production of the campaign's mass media and digital content.
Dissemination of crawl and media messages
Advocacy meeting held with religious and community leaders at entral level
Send letters to school, churches ,market committees
Media briefing at all levels and start of message broadcasting
Support for the organization of sound awareness caravans in big cities
Sends communication materials to the field
Mobilize women and Youth association
Mobilize Local resources for the campaign
Distribution of SMS messages to subscribers
training for central level supervisors
Central supervisors travel to the regions
Training of regional/district supervisors
Organization of advocacy meetings at regional/district level
Organization of community meetings at thE HF with all the community leaders
Orientation of Community Social Mobilisers, Town criers and develop the Mobilizer Deployment Plan (itinerary)
Door-to-door awareness-raising, household pre-marking and child counting by social mobilizers
Start with proximity supervision of front-line workers with ODK tools
Official national launch ceremony of the campaign
During the campaign | Official campaign launch ceremony in the regions/health districts
Continued door-to-door awareness-raising by social mobilizers
Continued proximity supervision of front-line workers with ODK tools
Daily collection, analysis, synthesis and sharing of social mobilization data
Managing refusal and reluctance cases
Vaccination follow-up in former refractory vaccianle households
Daily evaluation meetings at all levels | bar: Month 2 23
Daily collection and reporting of rumors and misinformation
After the campaign | Mapping of refusal cases to be managed between campaigns
Drawing up recovery plans at all level
Organization of communication data feedback meeting/participation in final evaluation meeting
Send letters of thanks to stakeholders
Conducting social investigations to understand the reasons for non-vaccination
Support activities to generate demand for immunization services